## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MUST HAVE | Dependency | Assignee | 3-Completed
S1 | S1 | US-001 | Project setup and environment configuration | MUST HAVE | No Dependency | Somana Uday Shankar | 3- Completed
S1 | S1 | US-002 | Data ingestion using APIs (Yahoo Finance) | MUST HAVE | API Access | Somana Uday Shankar | 3- Completed
S2 | S2 | US-003 | Data cleaning and preprocessing | MUST HAVE | Dataset | Somana Uday Shankar | 3- Completed
S2 | S2 | US-004 | Feature engineering for ML models | MUST HAVE | Data Processing | Somana Uday Shankar | 3- Completed
S3 | S3 | US-005 | Build ML models (Random Forest, Gradient Boosting) | MUST HAVE | Scikit-learn | Somana Uday Shankar | 3- Completed
S3 | S3 | US-006 | Signal generation logic (Buy/Sell/Hold) | MUST HAVE | ML Models | Somana Uday Shankar | 3- Completed
S4 | S4 | US-007 | Model training and evaluation | MUST HAVE | ML Pipeline | Somana Uday Shankar | 3- Completed
S5 | S5 | US-008 | Backtesting engine development | MUST HAVE | Historical Data | Somana Uday Shankar | 3- Completed
S5 | S5 | US-009 | Performance metrics calculation (Sharpe ratio, etc.) | SHOULD HAVE | Backtesting | Somana Uday Shankar | 3- Completed
S6 | S6 | US-010 | Real-time alert system (Email/Slack) | MUST HAVE | API Integration | Somana Uday Shankar | 3- Completed
S7 | S7 | US-011 | Dashboard development (Streamlit/Dash) | MUST HAVE | Frontend | Somana Uday Shankar | 2- In Progress
S8 | S8 | US-012 | Deployment and final testing | MUST HAVE | Cloud Platform | Somana Uday Shankar | 2- In Progress

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 75 | 22 | 12 | 11 | 9 | 7 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | 1 | Introduction to Project & Requirement Gathering | 2026-02-02 | 2026-02-03 | TVR Pranay,Uday Shankar | Others | 3-Completed | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 2 | Market Research (Stocks & ETF Analysis) | 2026-02-04 | 2026-02-06 | TVR Pranay, Rajitha | Research | 3-Completed | 4 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 3 | Define Signal Strategy (Indicators like RSI, MACD) | 2026-02-07 | 2026-02-09 | TVR Pranay | Design | 3-Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 4 | Setup Python Environment & Libraries | 2026-02-10 | 2026-02-11 | TVR Pranay,Uday Shankar, Vaihnavi. Salima, Rajitha | Setup | 3-Completed | 6 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 5 | Data Collection using APIs (Yahoo Finance, etc.) | 2026-02-12 | 2026-02-15 | TVR Pranay,Uday Shankar, Vaihnavi. Salima, Rajitha | Coding | 3-Completed | 12 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 6 | Data Preprocessing & Cleaning | 2026-02-16 | 2026-02-18 | TVR Pranay, Vasanthi | Coding | 3-Completed | 7 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 7 | Implement Technical Indicators (RSI, MACD, EMA) | 2026-02-19 | 2026-02-22 | TVR Pranay, Uday Shankar | Coding | 3-Completed | 10 | 3 | 0 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 8 | Generate Buy/Sell Signal Logic | 2026-02-23 | 2026-02-26 | TVR Pranay, Vaishnav, Salima | Coding | 3-Completed | 12 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 9 | Backtesting Strategy on Historical Data | 2026-02-27 | 2026-03-02 | TVR Pranay | Testing | 3-Completed | 12 | 4 | 3 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 10 | Basic Visualization (Graphs & Signals) | 2026-03-03 | 2026-03-05 | TVR Pranay, Uday Shankar | Build | 2-In Progress | 8 | Day 1: 3; Day 2: 0; Day 3: 1; Day 4: 1; Day 5: 1; Day 6: 1; Day 7: 1

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 2 | Day 6 | Difficulty in understanding stock data formats and API usage | Conducted research and referred documentation (yfinance) to clarify concepts
Sprint 2 | Day 7 | Issues in calculating technical indicators (RSI, Moving Average) | Debugged formulas and verified calculations with sample data
Sprint 3 | Day 12 | Confusion in designing accurate Buy/Sell signal logic | Discussed with team and refined signal conditions
Sprint3 | Day 16 | Errors during backtesting of trading strategy | Fixed logic issues and tested with different datasets
Sprint4 | Day 19 | Difficulty in integrating all modules (data, indicators, signals) | Performed step-by-step integration and resolved bugs
Sprint5 | Day 25 | Issues in final testing and visualization output | Improved graphs and validated final results

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-02-02 | 2026-02-03 | TVR Pranay, Somana Uday Shankar | Validate data from multiple APIs before processing | Assuming stock data sources are always accurate | Participating in team discussions and analysis | Verified data from multiple sources (Yahoo Finance, APIs) before use
2 | Sprint 2 | 2026-02-12 | 2026-02-15 | Shaik Salima , Vasanthi , TVR Pranay | Perform early testing after each module | Delaying testing of trading signals | Maintaining focus on coding and logic building | Completed signal generation module on time
3 | Sprint 3 | 2026-02-16 | 2026-02-18 | Rajitha Sajja, Vaishnavi Patel, Somana Uday Shankar | Optimize indicator calculations for accuracy | Rushing implementation of indicators (RSI, Moving Avg) | Asking for help when facing issues | Improved accuracy of indicators with team support
4 | Sprint 4 | 2026-02-19 | 2026-02-22 | Vasanthi , TVR Pranay, Rajitha Sajja | Handle missing and noisy data properly | Ignoring edge cases in market data | Collaborating on strategy development | Added validation checks for missing/invalid data
5 | Sprint 5 | 2026-03-03 | 2026-03-05 | Somana Uday Shankar,Vaishnavi Patel, Shaik Salima | Focus on better data visualization | Delaying visualization development | Working consistently on modules | Created basic graphs for signal visualization